## Sheet1
State | Delivery Route | Phase | RAG | Project Code | Project Name | Start Date | End Date | Previous End Date (last month) | Funding Status | Total Required Budget | Current Approved Investment Paper Value | Budget released to project | Total Spend To Date | Total Estimate at Completion | Portfolio Director | Project Manager
Active | Simple Project | Deployment | Green | PRJ6840 | Project 062 | 2023-09-19 | 2024-04-22 | 2024-04-22 | Approved (Full) | 28600 |  | 28600 | 23457 | 25457 | Monti Chandrasekaran | Michelo Singh
Active | Large Project | Feasibility | Green | PRJ6560 | Project 100 | 2023-11-20 | 2024-04-30 | 2024-04-30 | Approved (Full) | 50000 |  | 50000 | 39356 | 39916 | Mark Holland | Alexandra Mankowski
Active | Large Project | Deployment | Amber | PRJ4576 | Project 156 | 2020-06-29 | 2024-04-30 | 2024-04-30 | Approved (Supplemental) | 5200000 | 5200000 | 5066000 | 5089833 | 5095896 | Monti Chandrasekaran | Xuan Beckford-Jones
Active | Large Project | Closure | Green | PRJ6341 | Project 193 | 2023-01-16 | 2024-04-30 | 2024-04-30 | Approved (Full) | 690000 | 690000 | 658000 | 578256 | 630146 | Sreedhar Kishore | Ciro Gill
Active | Simple Project | Build | Green | PRJ6971 | Project 143 | 2024-02-18 | 2024-05-01 | 2024-05-01 | Approved (Full) | 35000 |  | 35000 | 13433 | 12059 | Enrico Sayimpu | Mayad M
Active | Large Project | Deployment | Green | PRJ6254 | Project 142 | 2023-06-19 | 2024-05-03 | 2024-05-03 | Approved (Full) | 748755 | 748755 | 588412 | 586925 | 585334 | Aidan Powell | Pravinraj Bajpai
Active | Simple Project | Deployment | Green | PRJ5734 | Project 097 | 2022-05-30 | 2024-05-03 | 2024-05-03 | Approved (Full) | 50360 | 42000 | 40000 | 39422 | 39329 | Enrico Sayimpu | Mayad M
Active | Simple Project | Planning & Design | Green | PRJ7019 | Project 066 | 2024-02-13 | 2024-05-10 | 2024-05-10 | Approved (Full) | 11625 |  | 11625 | 3844 | 5401 | Mark Holland | Claire Sunilkumar
Active | Flexible Scope Project | Delivery | Green | PRJ6544 | Project 133 | 2023-07-17 | 2024-05-10 | 2024-05-10 | Approved (Full) | 696000 | 696000 | 696000 | 688510 | 694149 | Nithinverghese Jackson | Madalina Raj
Active | Simple Project | Build | Green | PRJ6241 | Project 012 | 2022-10-13 | 2024-05-10 | 2024-05-10 | Approved (Full) | 77102 | 77200 | 77102 | 72770 | 69396 | Enrico Sayimpu | Anindita Azhukadu Philip
Active | Large Project | Deployment | Green | PRJ6536 | Project 202 | 2023-06-01 | 2024-05-10 | 2024-04-30 | Approved (Full) | 282318.96 | 282318.96 | 243000 | 212186 | 218946 | Sreedhar Kishore | Martin Singh Laller
Active | Large Project | Deployment | Green | PRJ6290 | Project 006 | 2022-11-21 | 2024-05-10 | 2024-05-10 | Approved (Full) | 394771 | 389271 | 324393 | 301481 | 305010 | Mark Holland | Neeti Chimata
Active | Large Project | Deployment | Green | PRJ6331 | Project 128 | 2022-12-19 | 2024-05-10 | 2024-05-10 | Approved (Supplemental) | 1489535 | 1739535 | 1453728 | 1365974 | 1382100 | Mark Holland | Gopikrishnan Wheat
Active | Simple Project | Deployment | Green | PRJ6485 | Project 077 | 2023-05-22 | 2024-05-16 | 2024-05-16 | Approved (Supplemental) | 457000 | 457000 | 375600 | 364840 | 375141 | Jason Hill | Preeti Prasanna
Active | Simple Project | Planning & Design | Green | PRJ6913 | Project 157 | 2024-01-18 | 2024-05-17 | 2024-05-17 | Seed Funding | 50000 |  | 10000 | 3190 | 3336 | Monti Chandrasekaran | Xuan Beckford-Jones
Active | Large Project | Build | Amber | PRJ6264 | Project 176 | 2022-11-14 | 2024-05-17 | 2024-05-17 | Approved (Full) | 284919 | 284919 | 264599 | 244105 | 264305 | Hariprasath Clark | Shashishekhar James
Active | Large Project | Deployment | Green | PRJ5367 | Project 041 | 2021-08-13 | 2024-05-17 | 2024-05-17 | Approved (Supplemental) | 4236273 | 4236273 | 4236145 | 4167738 | 4172342 | Mark Holland | Lisa Hanson-Abbott
Active | Simple Project | Deployment | Green | PRJ6850 | Project 169 | 2023-09-26 | 2024-05-17 | 2024-05-17 | Approved (Full) | 12000 |  | 12000 | 11937 | 11937 | Monti Chandrasekaran | Michelo Singh
Active | Simple Project | Deployment | Green | PRJ6750 | Project 108 | 2023-08-21 | 2024-05-20 | 2024-05-20 | Approved (Full) | 485000 | 485000 | 445789 | 437292 | 440254 | Aidan Powell | Ovidiu Sharma
Active | Simple Project | Build | Green | PRJ6725 | Project 208 | 2023-09-04 | 2024-05-24 | 2024-05-24 | Approved (Full) | 61888 | 61888 | 61888 | 50413 | 54464 | Sreedhar Kishore | Lalith Chandrasekaran
Active | Simple Project | Build | Green | PRJ6477 | Project 136 | 2023-08-17 | 2024-05-30 | 2024-05-30 | Approved (Full) | 75000 | 75000 | 63000 | 56544 | 57040 | Aidan Powell | Diksha Dash
Active | Large Project | Feasibility | Green | PRJ7040 | Project 063 | 2024-03-03 | 2024-05-31 | 2024-05-31 | Seed Funding | 50000 |  | 50000 | 873 | 17573 | Jason Hill | Nicolae Singh
Active | Flexible Scope Project | Mobilisation | Green | PRJ7038 | Project 021 | 2024-02-26 | 2024-05-31 | 2024-05-31 | Approved (Full) | 147000 | 147000 | 115000 | 195 | 146800 | Aidan Powell | Pravinraj Bajpai
Active | Simple Project | Planning & Design | Green | PRJ7009 | Project 058 | 2024-03-03 | 2024-05-31 | 2024-05-31 | Approved (Full) | 20000 |  | 12910 | 3203 | 1103 | Enrico Sayimpu | Madhurjya Anderton
Active | Simple Project | Planning & design | Green | PRJ6670 | Project 079 | 2023-09-01 | 2024-05-31 | 2024-05-01 | Seed Funding | 250000 |  | 50000 | 45741 | 47031 | Mark Holland | Claire Sunilkumar
Active | Simple Project | Planning & Design | Green | PRJ6832 | Project 168 | 2023-09-12 | 2024-05-31 | 2024-05-31 | Approved (Full) | 16000 |  | 16000 | 8880 | 15623 | Aidan Powell | Ovidiu Sharma
Active | Simple Project | Planning & Design | Green | PRJ7035 | Project 074 | 2024-03-07 | 2024-05-31 | 2024-05-31 | Approved (Full) | 35000 | 35000 | 35000 | 2033 | 27126 | Enrico Sayimpu | Robert Delport
Active | Simple Project | Planning & Design | Green | PRJ6969 | Project 001 | 2024-01-15 | 2024-05-31 | 2024-05-31 | Approved (Full) | 16125 |  | 16125 | 3403 | 5686 | Jason Hill | Adrian Das
Active | Simple Project | Planning & Design | Green | PRJ6947 | Project 101 | 2024-04-01 | 2024-05-31 | 2024-05-31 | Seed Funding | 20000 |  | 20000 | 0 | 10459 | Santosh Sonal | Inderpreet AlaguRam R
Active | Flexible Scope Project | Delivery | Green | PRJ6431 | Project 033 | 2023-09-01 | 2024-05-31 | 2024-05-31 | Approved (Full) | 400000 | 400000 | 400000 | 373540 | 397783 | Monti Chandrasekaran | Michelo Singh
Active | Large Project | Build | Green | PRJ6569 | Project 040 | 2023-08-21 | 2024-05-31 | 2024-05-31 | Approved (Full) | 292275 | 292275 | 261000 | 224789 | 234702 | Nithinverghese Jackson | Aney Sadowyj
Active | Simple Project | Build | Green | PRJ6877 | Project 027 | 2023-11-20 | 2024-05-31 | 2024-05-31 | Approved (Full) | 182579 | 182579 | 150000 | 83475 | 83290 | Nithinverghese Jackson | Madalina Raj
Active | Simple Project | Build | Green | PRJ6147 | Project 137 | 2022-10-27 | 2024-05-31 | 2024-05-31 | Approved (Full) | 22000 | 18374 | 17674 | 13634 | 16031 | Mark Holland | Leo Kumar Panapakkam Srinivasan
Active | Large Project | Deployment | Amber | PRJ6465 | Project 026 | 2023-03-17 | 2024-05-31 | 2024-05-31 | Approved (Full) | 2318510 | 2318510 | 1965400 | 1559000 | 1724614 | Sreedhar Kishore | Ciro Gill
Active | Simple Project | Deployment | Green | PRJ6336 | Project 080 | 2022-12-12 | 2024-05-31 | 2024-05-31 | Approved (Full) | 87412 | 87412 | 87412 | 86581 | 86826 | Monti Chandrasekaran | Michelo Singh
Active | Simple Project | Build | Green | PRJ6778 | Project 173 | 2024-01-03 | 2024-06-03 | 2024-06-03 | Approved (Full) | 118965 | 118965 | 118965 | 80476 | 118905 | Sreedhar Kishore | Lalith Chandrasekaran
Active | Simple Project | Planning & Design | Green | PRJ6993 | Project 167 | 2024-01-19 | 2024-06-07 | 2024-06-07 | Approved (Full) | 12375 |  | 10000 | 2042 | 5737 | Aidan Powell | Diksha Dash
Active | Simple Project | Build | Amber | PRJ6371 | Project 037 | 2023-02-20 | 2024-06-07 | 2024-06-07 | Approved (Full) | 95000 | 120000 | 95000 | 83255 | 91474 | Hariprasath Clark | Amanda Gabriela Spataru
Active | Large Project | Deployment | Green | PRJ6393 | Project 166 | 2023-02-27 | 2024-06-07 | 2024-06-07 | Approved (Full) | 232534 | 232534 | 232534 | 205016 | 213032 | Monti Chandrasekaran | Michelo Singh
In plan, not yet started | Simple Project | Not Started |  | PRJ7085 | Project 172 | 2024-04-18 | 2024-06-07 | 2024-06-07 | Not Yet Approved | 41055 |  | 0 | 0 | 0 | Enrico Sayimpu | Anindita Azhukadu Philip
Active | Large Project | Deployment | Red | PRJ6034 | Project 197 | 2022-11-21 | 2024-06-09 | 2024-06-09 | Approved (Full) | 941435 | 941435 | 941000 | 935224 | 936200 | Mark Holland | Neeti Chimata
Active | Simple Project | Planning & Design | Green | PRJ6616 | Project 052 | 2023-11-11 | 2024-06-14 | 2024-06-14 | Approved (Full) | 75000 | 75000 | 65000 | 30615 | 48750 | Hariprasath Clark | Iatsenko Tench
Active | Simple Project | Build | Green | PRJ6324 | Project 159 | 2022-12-05 | 2024-06-14 | 2024-05-17 | Seed Funding | 80000 |  | 30000 | 22467 | 48875 | Jason Hill | Preeti Prasanna
Active | Simple Project | Build | Green | PRJ6406 | Project 095 | 2023-05-08 | 2024-06-21 | 2024-06-21 | Approved (Full) | 300000 | 300000 | 279218 | 162388 | 225622 | Sreedhar Kishore | Ciro Gill
Active | Simple Project | Build | Green | PRJ6696 | Project 170 | 2023-07-05 | 2024-06-21 | 2024-06-21 | Approved (Full) | 124410 | 124410 | 99748 | 88047 | 93905 | Monti Chandrasekaran | Xuan Beckford-Jones
Active | Large Project | Planning & Design | Red | PRJ6808 | Project 144 | 2023-09-01 | 2024-06-26 | 2024-06-26 | Approved (Full) | 255000 | 255000 | 212500 | 168362 | 342380 | Nithinverghese Jackson | Aney Sadowyj
Active | Flexible Scope Project | Mobilisation | Amber | PRJ6501 | Project 034 | 2023-06-12 | 2024-06-28 | 2024-06-28 | Approved (Full) | 250000 | 171844 | 150000 | 129277 | 142675 | Aidan Powell | Krishan Henwood
Active | Flexible Scope Project | Delivery | Green | PRJ6920 | Project 069 | 2023-12-03 | 2024-06-28 | 2024-06-28 | Approved (Interim) | 375631 | 375631 | 311500 | 241730 | 311054 | Hariprasath Clark | Shashishekhar James
Active | Large Project | Build | Amber | PRJ4193 | Project 071 | 2022-04-04 | 2024-06-28 | 2024-06-28 | Approved (Full) | 304000 | 304000 | 304000 | 282652 | 303846 | Monti Chandrasekaran | Michelo Singh
Active | Simple Project | Build | Green | PRJ6518 | Project 206 | 2023-09-04 | 2024-06-28 | 2024-06-28 | Approved (Full) | 100000 | 100000 | 46000 | 37321 | 39074 | Sreedhar Kishore | Elena Martino
Active | Simple Project | Build | Amber | PRJ6618 | Project 053 | 2023-12-11 | 2024-06-28 | 2024-06-28 | Approved (Full) | 231900 | 231900 | 216900 | 119446 | 190439 | Nithinverghese Jackson | Pietro Ramachandran
Active | Simple Project | Build | Amber | PRJ5215 | Project 086 | 2021-05-20 | 2024-06-28 | 2024-06-28 | Approved (Full) | 48000 |  | 36000 | 20593 | 28725 | Hariprasath Clark | Iatsenko Tench
Active | Large Project | Deployment | Green | PRJ6184 | Project 207 | 2022-10-03 | 2024-06-28 | 2024-06-28 | Approved (Full) | 420000 | 420000 | 330000 | 276170 | 311166 | Mark Holland | Alexandra Mankowski
Active | Simple Project | Planning & Design | Green | PRJ6907 | Project 147 | 2023-12-01 | 2024-06-30 | 2024-06-30 | Seed Funding | 30000 |  | 30000 | 29303 | 29303 | Sreedhar Kishore | Elena Martino
In plan, not yet started | Large Project | Not Started |  | PRJ6660 | Project 057 | 2024-03-24 | 2024-06-30 | 2024-06-30 | Not Yet Approved | 250000 |  | 0 | 0 | 249840 | Monti Chandrasekaran | Xuan Beckford-Jones
In plan, not yet started | Simple Project | Not Started |  | PRJ7084 | Project 116 | 2024-04-22 | 2024-06-30 | 2024-06-30 | Not Yet Approved | 20000 |  | 0 | 0 | 0 | Jason Hill | Shubham Nallamuthu
In plan, not yet started | Simple Project | Not Started |  | PRJ6976 | Project 009 | 2024-04-01 | 2024-07-01 | 2024-07-01 | Not Yet Approved | 0 |  | 0 | 0 | 0 | Monti Chandrasekaran | Xuan Beckford-Jones
Active | Simple Project | Planning & Design | Green | PRJ6686 | Project 148 | 2023-12-10 | 2024-07-12 | 2024-07-12 | Approved (Full) | 250000 | 250000 | 250000 | 15110 | 226057 | Santosh Sonal | Nicola Delport
Active | Large Project | Deployment | Green | PRJ6379 | Project 163 | 2023-02-06 | 2024-07-12 | 2024-07-12 | Approved (Full) | 208000 | 208000 | 199000 | 166806 | 210460 | Nithinverghese Jackson | Aney Sadowyj
Active | Large Project | Feasibility | Green | PRJ6851 | Project 132 | 2023-12-08 | 2024-07-31 | 2024-07-31 | Approved (Interim) | 200000 | 200000 | 200000 | 116016 | 196408 | Aidan Powell | Krishan Henwood
Active | Simple Project | Planning & Design | Green | PRJ7055 | Project 042 | 2024-03-15 | 2024-07-31 | 2024-07-31 | Seed Funding | 22500 | 22500 | 15000 | 0 | 6000 | Monti Chandrasekaran | Xuan Beckford-Jones
Active | Flexible Scope Project | Delivery | Amber | PRJ6040 | Project 065 | 2023-10-19 | 2024-07-31 | 2024-07-31 | Approved (Full) | 472289 | 472289 | 411187 | 336972 | 497196 | Santosh Sonal | Marzia Bhalerao
Active | Simple Project | Build | Green | PRJ6909 | Project 186 | 2023-12-28 | 2024-07-31 | 2024-07-31 | Seed Funding | 57960 |  | 48300 | 23720 | 33082 | Aidan Powell | Ovidiu Sharma
In plan, not yet started | Large Project | Not Started |  | PRJ7014 | Project 023 | 2024-05-20 | 2024-07-31 | 2024-07-31 | Not Yet Approved | 75000 |  | 0 | 0 | 39997 | Jason Hill | Preeti Prasanna
Active | Large Project | Feasibility |  | PRJ7065 | Project 015 | 2024-05-07 | 2024-07-31 | 2024-07-31 | Seed Funding | 250000 |  | 50000 | 0 | 53189 | Jason Hill | Shubham Nallamuthu
In plan, not yet started | TBC | Not Started |  | PRJ6784 | Project 083 | 2024-05-01 | 2024-08-01 | 2024-08-01 | Not Yet Approved | 42495.39 |  | 0 | 0 | 0 | Monti Chandrasekaran | Xuan Beckford-Jones
Active | Large Project | Feasibility | Green | PRJ6027 | Project 090 | 2022-11-14 | 2024-08-02 | 2024-08-02 | Approved (Interim) | 500000 | 70000 | 70000 | 61541 | 253275 | Monti Chandrasekaran | Michelo Singh
Active | Large Project | Build | Green | PRJ6223 | Project 129 | 2022-10-03 | 2024-08-05 | 2024-08-05 | Approved (Full) | 101900 | 101900 | 82000 | 48690 | 90865 | Aidan Powell | Krishan Henwood
In plan, not yet started | Large Project | Not Started |  | PRJ6824 | Project 158 | 2024-04-01 | 2024-08-05 | 2024-08-05 | Not Yet Approved |  |  | 0 | 0 | 0 | Monti Chandrasekaran | Michelo Singh
Active | Large Project | Feasibility | Green | PRJ6999 | Project 114 | 2024-02-12 | 2024-08-11 | 2024-08-11 | Approved (Full) | 20000 |  | 20000 | 15149 | 20129 | Aidan Powell | Pravinraj Bajpai
Active | Simple Project | Planning & Design |  | PRJ7013 | Project 191 | 2024-03-11 | 2024-08-16 | 2024-08-16 | Seed Funding | 20500 |  | 20500 | 858 | 11851 | Monti Chandrasekaran | Michelo Singh
Active | Large Project | Build | Green | PRJ6023 | Project 024 | 2022-07-06 | 2024-08-19 | 2024-08-19 | Approved (Full) | 303979 | 303979 | 289638 | 164358 | 271018 | Mark Holland | Claire Sunilkumar
Active | Large Project | Build | Green | PRJ4775 | Project 085 | 2021-01-01 | 2024-08-19 | 2024-08-19 | Approved (Full) | 616000 | 616000 | 540000 | 387509 | 535100 | Aidan Powell | Diksha Dash
Active | Simple Project | Planning & Design | Green | PRJ6797 | Project 072 | 2023-11-16 | 2024-08-21 | 2024-08-21 | Seed Funding | 45000 |  | 5000 | 2832 | 40202 | Nithinverghese Jackson | Pietro Ramachandran
Active | Simple Project | Planning & Design | Green | PRJ7027 | Project 151 | 2024-03-10 | 2024-08-23 | 2024-08-23 | Approved (Full) | 84936 | 84936 | 15000 | 11616 | 65773 | Nithinverghese Jackson | Aney Sadowyj
Active | Large Project | Not Started |  | PRJ7024 | Project 112 | 2024-05-13 | 2024-08-23 | 2024-08-23 | Seed Funding | 100000 |  | 10000 | 0 | 16036 | Enrico Sayimpu | Akash Garofalo
In plan, not yet started | Large Project | Not Started |  | PRJ7032 | Project 180 | 2024-06-24 | 2024-08-23 | 2024-08-23 | Not Yet Approved | 250000 |  | 0 | 0 | 0 | Monti Chandrasekaran | Xuan Beckford-Jones
In plan, not yet started | Simple Project | Not Started |  | PRJ6580 | Project 039 | 2024-06-03 | 2024-08-23 | 2024-08-23 | Not Yet Approved | 250000 |  | 0 | 0 | 230393 | Mark Holland | Gopikrishnan Wheat
Active | Large Project | Feasibility | Green | PRJ6739 | Project 152 | 2023-10-02 | 2024-08-24 | 2024-08-24 | Approved (Full) | 243196 | 243196 | 45000 | 18169 | 234570 | Santosh Sonal | Judith Ramakrishnan
Active | Large Project | Build | Green | PRJ6735 | Project 154 | 2023-09-01 | 2024-08-24 | 2024-08-24 | Approved (Full) | 387000 | 387000 | 327000 | 210589 | 288198 | Mark Holland | Neeti Chimata
Active | Simple Project | Deployment | Green | PRJ6737 | Project 182 | 2023-09-21 | 2024-08-24 | 2024-08-24 | Approved (Full) | 2128000 | 2100000 | 2109422 | 1708335 | 2060860 | Jason Hill | Shubham Nallamuthu
In plan, not yet started | Simple Project | Not Started |  | PRJ7072 | Project 153 | 2024-06-16 | 2024-08-24 | 2024-08-24 | Approved (Full) | 359364 | 359364 | 0 | 0 | 359362 | Monti Chandrasekaran | Xuan Beckford-Jones
Active | Simple Project | Planning & Design | Green | PRJ6874 | Project 111 | 2024-04-22 | 2024-08-26 | 2024-08-26 | Seed Funding | 10000 |  | 10000 | 0 | 5952 | Jason Hill | Shubham Nallamuthu
Active | Large Project | Build | Green | PRJ6548 | Project 004 | 2023-09-18 | 2024-08-29 | 2024-08-29 | Approved (Interim) | 371462 | 371462 | 321570 | 152872 | 274631 | Monti Chandrasekaran | Michelo Singh
Active | Simple Project | Deployment | Green | PRJ5978 | Project 002 | 2022-07-04 | 2024-08-29 | 2024-08-29 | Approved (Full) | 1473698.6 | 1473698.6 | 1453448 | 1192405 | 1301085 | Aidan Powell | Diksha Dash
In plan, not yet started | Large Project | Not Started |  | PRJ7012 | Project 003 | 2024-05-31 | 2024-08-29 | 2024-08-29 | Not Yet Approved | 80000 |  | 0 | 0 | 0 | Aidan Powell | Pravinraj Bajpai
In plan, not yet started | Large Project | Not Started | Green | PRJ6360 | Project 211 | 2024-03-24 | 2024-08-29 | 2024-08-29 | Not Yet Approved | 200000 |  | 0 | 0 | 200000 | Mark Holland | Muthukumar Balasubramanian
Active | Large Project | Feasibility | Green | PRJ6361 | Project 028 | 2023-02-06 | 2024-08-30 | 2024-08-30 | Approved (Interim) | 204000 | 60000 | 60000 | 21051 | 180435 | Santosh Sonal | Judith Ramakrishnan
Active | Large Project | Feasibility | Red | PRJ6876 | Project 102 | 2023-12-11 | 2024-08-30 | 2024-08-30 | Seed Funding | 50000 |  | 20000 | 14504 | 36620 | Mark Holland | Gopikrishnan Wheat
Active | Large Project | Feasibility | Amber | PRJ6391 | Project 165 | 2023-04-14 | 2024-08-30 | 2024-08-30 | Seed Funding | 250000 |  | 50000 | 28760 | 247740 | Sreedhar Kishore | Jeena V
Active | Simple Project | Planning & Design | Green | PRJ6789 | Project 056 | 2024-03-04 | 2024-08-30 | 2024-08-30 | Seed Funding | 62000 |  | 10000 | 2089 | 52224 | Hariprasath Clark | Iatsenko Tench
Active | Simple Project | Planning & Design | Green | PRJ6959 | Project 049 | 2024-01-15 | 2024-08-30 | 2024-08-30 | Seed Funding | 127000 |  | 30000 | 16619 | 103911 | Sreedhar Kishore | Elena Martino
Active | Simple Project | Planning & Design | Amber | PRJ6910 | Project 149 | 2023-12-06 | 2024-08-30 | 2024-08-30 | Seed Funding | 58000 |  | 20000 | 12260 | 40272 | Sreedhar Kishore | Elena Martino
Active | Flexible Scope Project | Delivery | Green | PRJ6702 | Project 109 | 2023-09-01 | 2024-08-30 | 2024-08-30 | Approved (Interim) | 2125000 | 1000000 | 1000000 | 813619 | 1063234 | Aidan Powell | Diksha Dash
Active | Simple Project | Build | Green | PRJ6731 | Project 013 | 2023-07-31 | 2024-08-30 | 2024-08-30 | Approved (Full) | 106000 | 106000 | 96000 | 46108 | 79117 | Hariprasath Clark | Iatsenko Tench
Active | Simple Project | Deployment | Green | PRJ6362 | Project 203 | 2022-12-19 | 2024-08-30 | 2024-08-30 | Approved (Full) | 97400 | 82400 | 97400 | 87442 | 88570 | Nithinverghese Jackson | Pietro Ramachandran
In plan, not yet started | Flexible Scope Project | Not Started |  | PRJ6551 | Project 048 | 2024-05-20 | 2024-08-30 | 2024-08-30 | Not Yet Approved | 541000 |  | 0 | 0 | 319968 | Monti Chandrasekaran | Michelo Singh
In plan, not yet started | Simple Project | Not Started |  | PRJ6490 | Project 161 | 2024-05-01 | 2024-08-30 | 2024-08-30 | Not Yet Approved | 25000 |  | 0 | 0 | 0 | Mark Holland | Lisa Hanson-Abbott
In plan, not yet started | Simple Project | Not Started |  | PRJ7051 | Project 043 | 2024-05-01 | 2024-08-30 | 2024-08-30 | Approved (Full) | 30000 |  | 0 | 0 | 0 | Hariprasath Clark | Andrew Andriesei
Active | Large Project | Feasibility | Green | PRJ6684 | Project 078 | 2024-03-18 | 2024-08-31 | 2024-08-31 | Seed Funding | 50000 |  | 10000 | 0 | 48000 | Jason Hill | Preeti Prasanna
Active | Large Project | Feasibility | Green | PRJ6673 | Project 192 | 2023-11-01 | 2024-08-31 | 2024-08-31 | Seed Funding | 200000 |  | 50000 | 45889 | 188892 | Aidan Powell | Ovidiu Sharma
Active | Large Project | Feasibility | Green | PRJ6674 | Project 005 | 2024-01-22 | 2024-08-31 | 2024-08-31 | Seed Funding | 150000 |  | 25000 | 700 | 138450 | Mark Holland | Alexandra Mankowski
Active | Large Project | Feasibility | Green | PRJ6682 | Project 141 | 2024-02-05 | 2024-08-31 | 2024-08-31 | Seed Funding | 100000 |  | 25000 | 13400 | 110330 | Hariprasath Clark | Amanda Gabriela Spataru
Active | Large Project | Feasibility |  | PRJ7067 | Project 110 | 2024-04-23 | 2024-08-31 | 2024-08-31 | Seed Funding | 20000 |  | 20000 | 0 | 31440 | Jason Hill | Nicolae Singh
Active | Large Project | Feasibility |  | PRJ7028 | Project 134 | 2024-04-10 | 2024-08-31 | 2024-08-31 | Approved (Full) | 50000 | 50000 | 50000 | 10080 | 15060 | Hariprasath Clark | Amanda Gabriela Spataru
Active | Large Project | Feasibility | Green | PRJ6919 | Project 088 | 2024-02-04 | 2024-08-31 | 2024-08-31 | Approved (Full) | 1822843 | 1822843 | 420000 | 142935 | 1648538 | Hariprasath Clark | Iatsenko Tench
Active | Large Project | Feasibility | Green | PRJ3501 | Project 190 | 2023-09-18 | 2024-08-31 | 2024-08-31 | Approved (Interim) | 555600 | 100000 | 65000 | 60331 | 544994 | Santosh Sonal | Saurav Clark
Active | Flexible Scope Project | Mobilisation | Green | PRJ6621 | Project 054 | 2023-09-01 | 2024-08-31 | 2024-08-31 | Approved (Full) | 60000 | 60000 | 60000 | 21693 | 60000 | Santosh Sonal | Kumanaraj Hunnisett
Active | Flexible Scope Project | Mobilisation |  | PRJ7030 | Project 096 | 2024-03-01 | 2024-08-31 | 2024-08-31 | Approved (Full) | 1935000 | 1935000 | 572000 | 3000 | 1735123 | Santosh Sonal | Saurav Clark
Active | Flexible Scope Project | Mobilisation | Green | PRJ6558 | Project 200 | 2024-01-01 | 2024-08-31 | 2024-08-31 | Seed Funding | 300000 |  | 50000 | 128 | 300128 | Hariprasath Clark | Shashishekhar James
Active | Large Project | Planning & Design | Green | PRJ6672 | Project 092 | 2024-01-08 | 2024-08-31 | 2024-08-31 | Seed Funding | 100000 |  | 30000 | 4095 | 42145 | Santosh Sonal | Kumanaraj Hunnisett
Active | Large Project | Planning & Design | Green | PRJ6630 | Project 210 | 2024-01-09 | 2024-08-31 | 2024-08-31 | Seed Funding | 150000 |  | 25000 | 43065 | 130845 | Mark Holland | Muthukumar Balasubramanian
Active | Large Project | Planning & Design | Amber | PRJ6755 | Project 135 | 2023-11-01 | 2024-08-31 | 2024-08-31 | Approved (Interim) | 816000 | 120000 | 91000 | 62572 | 223899 | Aidan Powell | Pravinraj Bajpai
Active | Large Project | Planning & Design | Green | PRJ6689 | Project 076 | 2023-08-01 | 2024-08-31 | 2024-08-31 | Approved (Full) | 1700000 | 1700000 | 1603000 | 343368 | 1473913 | Nithinverghese Jackson | Pietro Ramachandran
Active | Simple Project | Planning & Design | Green | PRJ6578 | Project 045 | 2023-10-20 | 2024-08-31 | 2024-08-31 | Seed Funding | 30000 |  | 30000 | 12546 | 22252 | Hariprasath Clark | Iatsenko Tench
Active | Simple Project | Planning & Design | Green | PRJ6607 | Project 198 | 2023-12-04 | 2024-08-31 | 2024-08-31 | Seed Funding | 50000 |  | 20000 | 10159 | 33895 | Mark Holland | Leo Kumar Panapakkam Srinivasan
Active | Simple Project | Planning & Design | Green | PRJ6627 | Project 075 | 2023-11-20 | 2024-08-31 | 2024-08-31 | Seed Funding | 190000 |  | 50000 | 32739 | 228402 | Enrico Sayimpu | Ashley Kandhasamy
Active | Simple Project | Planning & design | Green | PRJ6357 | Project 179 | 2023-01-09 | 2024-08-31 | 2024-08-31 | Seed Funding | 38750 |  | 38750 | 25714 | 113164 | Jason Hill | Adrian Das
Active | Flexible Scope Project | Delivery | Amber | PRJ6763 | Project 022 | 2023-09-01 | 2024-08-31 | 2024-08-31 | Approved (Full) | 372000 | 372000 | 372000 | 231399 | 357676 | Enrico Sayimpu | Andrew Ammanath
Active | Flexible Scope Project | Delivery | Green | PRJ6768 | Project 047 | 2023-12-11 | 2024-08-31 | 2024-08-31 | Approved (Full) | 176395.97 | 176395.97 | 140212.51 | 94521 | 174623 | Mark Holland | Neeti Chimata
Active | Flexible Scope Project | Delivery | Green | PRJ6655 | Project 036 | 2023-10-02 | 2024-08-31 | 2024-08-31 | Approved (Full) | 300000 | 300000 | 50000 | 68797 | 300046 | Nithinverghese Jackson | Madalina Raj
Active | Flexible Scope Project | Delivery | Amber | PRJ6161 | Project 188 | 2022-11-04 | 2024-08-31 | 2024-08-31 | Approved (Full) | 1082232 | 1082232 | 820710 | 783903 | 922745 | Sreedhar Kishore | Martin Singh Laller
Active | Flexible Scope Project | Delivery | Amber | PRJ6162 | Project 070 | 2022-11-01 | 2024-08-31 | 2024-08-31 | Approved (Full) | 1602615 | 1602615 | 1407130 | 1289231 | 1560406 | Monti Chandrasekaran | Michelo Singh
Active | Flexible Scope Project | Delivery | Green | PRJ6557 | Project 050 | 2023-09-01 | 2024-08-31 | 2024-08-31 | Approved (Full) | 360000 | 360000 | 267000 | 208910 | 767985 | Nithinverghese Jackson | Aney Sadowyj
Active | Flexible Scope Project | Delivery | Green | PRJ6623 | Project 055 | 2023-09-01 | 2024-08-31 | 2024-08-31 | Approved (Full) | 160000 | 160000 | 120000 | 93822 | 160000 | Sreedhar Kishore | Martin Singh Laller
Active | Flexible Scope Project | Delivery | Green | PRJ6615 | Project 051 | 2023-09-01 | 2024-08-31 | 2024-08-31 | Approved (Full) | 200000 | 300000 | 100000 | 94687 | 200000 | Enrico Sayimpu | Ashley Kandhasamy
Active | Flexible Scope Project | Delivery | Green | PRJ6946 | Project 010 | 2023-12-18 | 2024-08-31 | 2024-08-31 | Approved (Full) | 1276000 | 1211000 | 874480 | 518096 | 1153928 | Enrico Sayimpu | Michelle Swain
Active | Flexible Scope Project | Delivery | Green | PRJ6727 | Project 016 | 2023-09-01 | 2024-08-31 | 2024-08-31 | Approved (Full) | 6150000 | 6400000 | 6075000 | 2754118 | 3421969 | Jason Hill | Nicolae Singh
Active | Flexible Scope Project | Delivery | Green | PRJ6617 | Project 175 | 2023-08-21 | 2024-08-31 | 2024-08-31 | Seed Funding | 170000 |  | 50000 | 39456 | 45816 | Jason Hill | Adrian Das
Active | Flexible Scope Project | Delivery | Green | PRJ6787 | Project 130 | 2023-09-01 | 2024-08-31 | 2024-08-31 | Approved (Full) | 241122.47 | 241038 | 183334 | 133190 | 213621 | Mark Holland | Alexandra Mankowski
Active | Flexible Scope Project | Delivery | Green | PRJ6779 | Project 178 | 2023-09-01 | 2024-08-31 | 2024-08-31 | Seed Funding | 89801.59 |  | 50000 | 49017 | 77017 | Jason Hill | Shubham Nallamuthu
Active | Flexible Scope Project | Delivery | Green | PRJ6554 | Project 185 | 2023-11-20 | 2024-08-31 | 2024-08-31 | Approved (Full) | 285000 | 285000 | 285000 | 51833 | 278163 | Mark Holland | Claire Sunilkumar
Active | Flexible Scope Project | Delivery | Green | PRJ6555 | Project 035 | 2023-09-01 | 2024-08-31 | 2024-08-31 | Approved (Full) | 1630000 | 1630000 | 1630000 | 1473282 | 1519859 | Aidan Powell | Ovidiu Sharma
Active | Flexible Scope Project | Delivery | Green | PRJ6764 | Project 103 | 2023-09-01 | 2024-08-31 | 2024-08-31 | Approved (Full) | 253683.7 | 253683.7 | 157672.33 | 89038 | 227576 | Hariprasath Clark | Andrew Andriesei
Active | Large Project | Build | Red | PRJ5251 | Project 138 | 2021-06-07 | 2024-08-31 | 2024-08-31 | Approved (Supplemental) | 13800300 | 13800300 | 12710412 | 12268735 | 13338366 | Jason Hill | Shubham Nallamuthu
Active | Large Project | Build | Green | PRJ6629 | Project 081 | 2024-02-01 | 2024-08-31 | 2024-08-31 | Not Yet Approved | 150000 |  | 0 | 0 | 50000 | Monti Chandrasekaran | Michelo Singh
Active | Flexible Scope Project | Build | Green | PRJ6671 | Project 184 | 2024-02-01 | 2024-08-31 | 2024-08-31 | Seed Funding | 100000 |  | 10000 | 0 | 38134 | Sreedhar Kishore | Jeena V
Active | Simple Project | Build | Green | PRJ6766 | Project 046 | 2024-01-01 | 2024-08-31 | 2024-08-31 | Approved (Full) | 300265.16 | 300265.15 | 265548.53 | 137994 | 255181 | Sreedhar Kishore | Ciro Gill
Active | Simple Project | Build | Green | PRJ6576 | Project 171 | 2024-03-18 | 2024-08-31 | 2024-08-31 | Approved (Full) | 31000 | 31000 | 31000 | 1013 | 30919 | Sreedhar Kishore | Martin Singh Laller
Active | Simple Project | Build | Green | PRJ6637 | Project 189 | 2024-01-08 | 2024-08-31 | 2024-08-31 | Approved (Full) | 795000 | 795000 | 795000 | 257061 | 787061 | Sreedhar Kishore | Lalith Chandrasekaran
Active | Large Project | Deployment | Green | PRJ4536 | Project 155 | 2020-06-01 | 2024-08-31 | 2024-08-31 | Approved (Full) | 424000 | 424000 | 385759 | 342904 | 367612 | Jason Hill | Adrian Das
Active | Simple Project | Deployment | Green | PRJ6061 | Project 064 | 2022-12-05 | 2024-08-31 | 2024-08-31 | Approved (Full) | 2782395 | 2782395 | 2486678.7 | 2052812 | 2281428 | Hariprasath Clark | Shashishekhar James
In plan, not yet started | Simple Project | Planning & Design |  | PRJ6783 | Project 087 | 2024-06-03 | 2024-08-31 | 2024-08-31 | Approved (Full) | 90603 | 90603 | 0 | 0 | 82219 | Mark Holland | Lisa Hanson-Abbott
In plan, not yet started | Large Project | Not Started |  | PRJ6829 | Project 082 | 2024-06-02 | 2024-08-31 | 2024-08-31 | Seed Funding | 100000 |  | 50000 | 0 | 97400 | Mark Holland | Claire Sunilkumar
In plan, not yet started | Large Project | Not Started |  | PRJ6604 | Project 073 | 2024-06-10 | 2024-08-31 | 2024-08-31 | Not Yet Approved | 140000 |  | 0 | 0 | 50000 | Monti Chandrasekaran | Xuan Beckford-Jones
In plan, not yet started | Large Project | Not Started |  | PRJ6546 | Project 174 | 2024-03-18 | 2024-08-31 | 2024-08-31 | Seed Funding | 220000 |  | 50000 | 0 | 200000 | Sreedhar Kishore | Ciro Gill
In plan, not yet started | Large Project | Not Started |  | PRJ6692 | Project 098 | 2024-04-01 | 2024-08-31 | 2024-08-31 | Not Yet Approved | 416000 |  | 0 | 0 | 100000 | Aidan Powell | Pravinraj Bajpai
In plan, not yet started | Large Project | Not Started |  | PRJ6901 | Project 099 | 2024-05-01 | 2024-08-31 | 2024-08-31 | Not Yet Approved | 300000 |  | 0 | 0 | 0 | Monti Chandrasekaran | Xuan Beckford-Jones
In plan, not yet started | Flexible Scope Project | Not Started | Green | PRJ6683 | Project 008 | 2024-03-04 | 2024-08-31 | 2024-08-31 | Not Yet Approved | 50000 |  | 0 | 0 | 50000 | Aidan Powell | Ovidiu Sharma
In plan, not yet started | Simple Project | Not Started |  | PRJ7061 | Project 044 | 2024-05-20 | 2024-08-31 | 2024-08-31 | Not Yet Approved | 50000 |  | 0 | 0 | 1440 | Enrico Sayimpu | Akash Garofalo
In plan, not yet started | TBC | Not Started |  | PRJ6777 | Project 084 | 2024-06-03 | 2024-08-31 | 2024-08-31 | Not Yet Approved | 84188.99 |  | 0 | 0 | 0 | Mark Holland | Neeti Chimata
In plan, not yet started | TBC | Not Started |  | PRJ6770 | Project 145 | 2024-05-01 | 2024-08-31 | 2024-08-31 | Not Yet Approved | 240539.96 |  | 0 | 0 | 0 | Monti Chandrasekaran | Xuan Beckford-Jones
Active | Simple Project | Planning & Design | Green | PRJ6610 | Project 030 | 2023-11-16 | 2024-09-26 | 2024-09-26 | Seed Funding | 50000 |  | 15000 | 7597 | 46341 | Santosh Sonal | Nicola Delport
Active | Large Project | Deployment | Amber | PRJ4796 | Project 195 | 2020-09-28 | 2024-09-27 | 2024-09-27 | Approved (Full) | 2599000 | 2599000 | 2571643 | 2225595 | 2274315 | Jason Hill | Adrian Das
Active | Large Project | Planning & Design | Green | PRJ6752 | Project 183 | 2023-08-21 | 2024-09-30 | 2024-09-30 | Approved (Full) | 860000 | 860000 | 120000 | 105381 | 755718 | Santosh Sonal | Kumanaraj Hunnisett
Active | Flexible Scope Project | Delivery | Green | PRJ6760 | Project 038 | 2024-02-27 | 2024-09-30 | 2024-09-30 | Approved (Full) | 5600000 | 5638488 | 2685000 | 1316231 | 5126252 | Sreedhar Kishore | Jeena V
Active | Large Project | Feasibility | Green | PRJ7056 | Project 199 | 2024-03-17 | 2024-09-30 | 2024-09-30 | Seed Funding | 150000 |  | 20000 | 29500 | 64000 | Hariprasath Clark | Iatsenko Tench
In plan, not yet started | Large Project | Not Started |  | PRJ6572 | Project 089 | 2024-05-20 | 2024-09-30 | 2024-09-30 | Not Yet Approved | 500000 |  | 0 | 0 | 218065 | Nithinverghese Jackson | Pietro Ramachandran
In plan, not yet started | Simple Project | Not Started |  | PRJ6996 | Project 091 | 2024-07-21 | 2024-10-17 | 2024-10-17 | Not Yet Approved | 350000 |  | 0 | 0 | 0 | Jason Hill | Nicolae Singh
In plan, not yet started | Large Project | Not Started |  | PRJ6734 | Project 029 | 2024-06-17 | 2024-10-26 | 2024-10-26 | Not Yet Approved | 100000 |  | 0 | 0 | 60473 | Santosh Sonal | Judith Ramakrishnan
Active | Large Project | Feasibility | Green | PRJ7043 | Project 105 | 2024-04-08 | 2024-10-30 | 2024-10-30 | Seed Funding | 227000 |  | 40000 | 644 | 125902 | Jason Hill | Preeti Prasanna
Active | Flexible Scope Project | Mobilisation | Amber | PRJ6980 | Project 032 | 2024-02-26 | 2024-10-31 | 2024-10-31 | Approved (Full) | 70000 | 70000 | 70000 | 14702 | 67406 | Hariprasath Clark | Amanda Gabriela Spataru
Active | Simple Project | Planning & Design | Green | PRJ6497 | Project 113 | 2023-07-31 | 2024-10-31 | 2024-10-31 | Seed Funding | 687600 |  | 15000 | 7082 | 603393 | Aidan Powell | Pravinraj Bajpai
Active | Simple Project | Build | Green | PRJ6889 | Project 068 | 2023-12-18 | 2024-10-31 | 2024-10-31 | Approved (Full) | 38434 | 38434 | 34083 | 1006 | 34466 | Monti Chandrasekaran | Michelo Singh
In plan, not yet started | Large Project | Not Started |  | PRJ6827 | Project 162 | 2024-05-05 | 2024-10-31 | 2024-10-31 | Not Yet Approved |  |  | 0 | 0 | 0 | Mark Holland | Claire Sunilkumar
In plan, not yet started | Large Project | Not Started |  | PRJ6528 | Project 160 | 2024-05-05 | 2024-10-31 | 2024-10-31 | Not Yet Approved | 250000 |  | 0 | 0 | 0 | Jason Hill | Shubham Nallamuthu
In plan, not yet started | Simple Project | Not Started |  | PRJ6527 | Project 164 | 2024-05-05 | 2024-10-31 | 2024-10-31 | Not Yet Approved | 20000 |  | 0 | 0 | 0 | Jason Hill | Adrian Das
Active | Flexible Scope Project | Delivery | Green | PRJ6524 | Project 094 | 2023-08-21 | 2024-11-01 | 2024-11-01 | Approved (Full) | 6499905 | 6475000 | 6475000 | 4968180 | 6430709 | Mark Holland | Muthukumar Balasubramanian
In plan, not yet started | Flexible Scope Project | Not Started |  | PRJ6977 | Project 093 | 2024-05-19 | 2024-11-01 | 2024-11-01 | Approved (Full) | 1999996 | 1999996 | 50000 | 0 | 1948733 | Nithinverghese Jackson | Aney Sadowyj
Active | Simple Project | Planning & Design | Green | PRJ7006 | Project 187 | 2024-02-18 | 2024-11-28 | 2024-11-28 | Seed Funding | 50000 |  | 10000 | 3690 | 44219 | Santosh Sonal | Akeel Subramaniam
Active | Simple Project | Planning & Design | Green | PRJ7007 | Project 205 | 2024-02-12 | 2024-11-28 | 2024-11-28 | Seed Funding | 50000 |  | 10000 | 3439 | 55901 | Sreedhar Kishore | Martin Singh Laller
Active | Large Project | Planning & Design | Amber | PRJ6559 | Project 177 | 2023-11-27 | 2024-11-30 | 2024-08-31 | Seed Funding | 520000 |  | 50000 | 34073 | 495073 | Santosh Sonal | Marzia Bhalerao
Active | Simple Project | Planning & Design | Green | PRJ6481 | Project 115 | 2023-10-23 | 2024-11-30 | 2024-11-30 | Seed Funding | 100000 |  | 30000 | 25901 | 35234 | Nithinverghese Jackson | Aney Sadowyj
Active | Simple Project | Build | Green | PRJ6801 | Project 181 | 2023-10-11 | 2024-11-30 | 2024-11-30 | Approved (Full) | 100760 | 108098 | 90000 | 74757 | 81004 | Sreedhar Kishore | Ciro Gill
Active | Large Project | Build | Red | PRJ5884 | Project 194 | 2022-07-15 | 2024-12-06 | 2024-12-06 | Approved (Full) | 4000000 | 4000000 | 3759671 | 3543111 | 4129019 | Nithinverghese Jackson | Pietro Ramachandran
In plan, not yet started | Large Project | Not Started |  | PRJ7031 | Project 150 | 2024-07-21 | 2024-12-20 | 2024-12-20 | Not Yet Approved | 155000 |  | 0 | 0 | 102135 | Monti Chandrasekaran | Michelo Singh
Active | Large Project | Feasibility | Amber | PRJ6549 | Project 196 | 2023-11-13 | 2025-01-17 | 2025-01-17 | Seed Funding | 150000 |  | 50000 | 42930 | 143848 | Enrico Sayimpu | Mayad M
Active | Simple Project | Build | Red | PRJ6507 | Project 139 | 2023-06-01 | 2025-01-17 | 2025-01-17 | Approved (Full) | 140000 |  | 35000 | 30082 | 141848 | Enrico Sayimpu | Ashley Kandhasamy
Active | Flexible Scope Project | Mobilisation | Green | PRJ6921 | Project 104 | 2023-12-10 | 2025-01-31 | 2025-01-31 | Seed Funding | 200000 |  | 25000 | 9461 | 17809 | Nithinverghese Jackson | Aney Sadowyj
Active | Large Project | Feasibility | Green | PRJ7005 | Project 106 | 2024-04-11 | 2025-02-13 | 2025-02-13 | Seed Funding | 150000 |  | 50000 | 2896 | 146748 | Monti Chandrasekaran | Xuan Beckford-Jones
Active | Large Project | Feasibility | Green | PRJ6570 | Project 059 | 2024-04-08 | 2025-02-28 | 2025-02-28 | Seed Funding | 380000 |  | 50000 | 3956 | 344918 | Sreedhar Kishore | Elena Martino
Active | Large Project | Feasibility | Green | PRJ6875 | Project 140 | 2024-02-27 | 2025-02-28 | 2025-02-28 | Seed Funding | 556000 |  | 50000 | 24082 | 534378 | Aidan Powell | Diksha Dash
In plan, not yet started | Flexible Scope Project | Not Started |  | PRJ6732 | Project 031 | 2024-05-22 | 2025-02-28 | 2025-02-28 | Not Yet Approved | 762400 |  | 0 | 0 | 742480 | Nithinverghese Jackson | Aney Sadowyj
In plan, not yet started | Large Project | Not Started |  | PRJ6911 | Project 107 | 2024-06-24 | 2025-03-13 | 2025-03-13 | Not Yet Approved | 81000 |  | 0 | 0 | 58760 | Enrico Sayimpu | Andrew Ammanath
Active | Flexible Scope Project | Delivery | Green | PRJ6728 | Project 209 | 2023-08-01 | 2025-03-22 | 2025-03-22 | Approved (Full) | 3718000 | 3718000 | 3718000 | 290878 | 3705172 | Nithinverghese Jackson | Madalina Raj
In plan, not yet started | Large Project | Not Started |  | PRJ6912 | Project 067 | 2024-06-16 | 2025-03-27 | 2025-03-27 | Not Yet Approved | 135000 |  | 0 | 0 | 88424 | Monti Chandrasekaran | Xuan Beckford-Jones
Active | Flexible Scope Project | Mobilisation | Amber | PRJ6543 | Project 011 | 2023-07-10 | 2025-06-30 | 2025-06-30 | Seed Funding | 300000 |  | 50000 | 49817 | 49817 | Nithinverghese Jackson | Aney Sadowyj
In plan, not yet started | Flexible Scope Project | Not Started |  | PRJ7078 | Project 014 | 2024-05-19 | 2025-07-31 | 2025-07-31 | Not Yet Approved | 1500000 |  | 0 | 0 | 0 | Hariprasath Clark | Amanda Gabriela Spataru
Active | Large Project | Feasibility | Red | PRJ6988 | Project 123 | 2024-02-08 | 2025-08-29 | 2025-08-29 | Approved (interim) | 150000 | 150000 | 150000 | 24639 | 864058 | Monti Chandrasekaran | Michelo Singh
Active | Large Project | Planning & Design | Green | PRJ6990 | Project 125 | 2024-02-08 | 2025-08-29 | 2025-08-29 | Approved (interim) | 100000 | 100000 | 100000 | 50764 | 144099 | Santosh Sonal | Akeel Subramaniam
Active | Large Project | Planning & Design | Amber | PRJ6984 | Project 120 | 2024-02-08 | 2025-08-29 | 2025-08-29 | Approved (interim) | 50000 | 50000 | 290000 | 44591 | 738888 | Hariprasath Clark | Andrew Andriesei
Active | Large Project | Planning & Design | Amber | PRJ6985 | Project 121 | 2024-02-08 | 2025-08-29 | 2025-08-29 | Approved (interim) | 50000 | 50000 | 50000 | 19121 | 581724 | Aidan Powell | Pravinraj Bajpai
Active | Large Project | Planning & Design | Amber | PRJ6986 | Project 126 | 2024-01-29 | 2025-08-29 | 2025-08-29 | Approved (interim) | 100000 | 100000 | 100000 | 32069 | 103307 | Santosh Sonal | Akeel Subramaniam
Active | Large Project | Planning & Design | Amber | PRJ6987 | Project 124 | 2024-02-08 | 2025-08-29 | 2025-08-29 | Approved (interim) | 50000 | 50000 | 50000 | 11850 | 165918 | Aidan Powell | Ovidiu Sharma
Active | Simple Project | Planning & Design | Amber | PRJ6991 | Project 127 | 2024-02-08 | 2025-08-29 | 2025-08-29 | Approved (interim) | 50000 | 50000 | 50000 | 3535 | 218451 | Mark Holland | Muthukumar Balasubramanian
Active | Simple Project | Deployment | Green | PRJ6237 | Project 212 | 2022-10-01 | 2025-08-29 | 2025-08-29 | Approved (Full) | 1621567 | 2464701 | 1621567 | 1280722 | 1610927 | Hariprasath Clark | Iatsenko Tench
Active | Large Project | Feasibility | Red | PRJ5795 | Project 119 | 2022-09-12 | 2025-08-31 | 2025-08-31 | Approved (Full) | 28548000 | 52696971 | 28548000 | 9637674 | 23583032 | Santosh Sonal | Judith Ramakrishnan
Active | Large Project | Feasibility | Green | PRJ5407 | Project 060 | 2021-10-04 | 2025-08-31 | 2025-08-31 | Approved (Interim) | 1161500 | 911500 | 911500 | 800306 | 882546 | Monti Chandrasekaran | Michelo Singh
Active | Flexible Scope Project | Mobilisation | Green | PRJ6640 | Project 201 | 2024-01-07 | 2025-08-31 | 2024-08-31 | Approved (Full) | 3600000 | 1620000 | 1020000 | 477734 | 3997670 | Nithinverghese Jackson | Madalina Raj
Active | Large Project | Planning & Design | Red | PRJ6892 | Project 117 | 2024-01-01 | 2025-08-31 | 2025-08-31 | Approved (interim) | 3400000 | 3400000 | 3400000 | 1464624 | 3609627 | Santosh Sonal | Akeel Subramaniam
Active | Large Project | Planning & Design | Amber | PRJ6894 | Project 122 | 2023-12-18 | 2025-08-31 | 2025-08-31 | Approved (interim) | 15000000 | 15000000 | 4932000 | 362363 | 8144291 | Hariprasath Clark | Shashishekhar James
Active | Large Project | Planning & Design | Amber | PRJ5771 | Project 204 | 2023-03-06 | 2025-08-31 | 2025-08-31 | Approved (interim) | 7146013 | 7146010 | 1600000 | 853448 | 7044864 | Sreedhar Kishore | Martin Singh Laller
Active | Simple Project | Planning & Design | Red | PRJ6893 | Project 118 | 2024-01-01 | 2025-08-31 | 2025-08-31 | Approved (interim) | 11600000 | 11600000 | 4600000 | 2489336 | 9808646 | Santosh Sonal | Marzia Bhalerao
In plan, not yet started | Large Project | Not Started |  | PRJ6577 | Project 007 | 2024-09-01 | 2025-08-31 | 2025-08-31 | Not Yet Approved | 150000 |  | 0 | 0 | 149790 | Hariprasath Clark | Amanda Gabriela Spataru
In plan, not yet started | Large Project | Not Started |  | PRJ6810 | Project 025 | 2024-09-01 | 2025-08-31 | 2025-08-31 | Not Yet Approved | 270000 |  | 0 | 0 | 140000 | Santosh Sonal | Marzia Bhalerao
In plan, not yet started | Large Project | Not Started |  | PRJ6547 | Project 131 | 2024-09-01 | 2025-08-31 | 2025-08-31 | Not Yet Approved | 250000 |  | 0 | 0 | 220000 | Nithinverghese Jackson | Pietro Ramachandran
In plan, not yet started | Large Project | Not Started |  | PRJ7039 | Project 061 | 2024-04-26 | 2025-10-03 | 2025-10-03 | Not Yet Approved | 587000 |  | 0 | 0 | 2831519 | Enrico Sayimpu | Mayad M
Active | Large Project | Build | Amber | PRJ5895 | Project 146 | 2022-05-23 | 2025-11-30 | 2025-11-30 | Approved (Full) | 7319545 | 8178359 | 5615000 | 1473185 | 5440470 | Mark Holland | Leo Kumar Panapakkam Srinivasan
Active | Large Project | Feasibility | Green | PRJ6895 | Project 017 | 2024-01-21 | 2026-06-30 | 2026-06-30 | Approved (Full) | 103432184 | 103432184 | 3293605 | 1184536 | 6739642 | Nithinverghese Jackson | Pietro Ramachandran
In plan, not yet started | Large Project | Not Started |  | PRJ7087 | Project 018 | 2024-05-05 | 2026-07-31 | 2026-06-30 | Not Yet Approved |  |  | 0 | 0 | 0 | Santosh Sonal | Saurav Clark
In plan, not yet started | Large Project | Not Started |  | PRJ7088 | Project 020 | 2024-05-05 | 2026-08-28 | 2026-06-30 | Not Yet Approved |  |  | 0 | 0 | 0 | Santosh Sonal | Marzia Bhalerao
In plan, not yet started | Large Project | Not Started |  | PRJ7086 | Project 019 | 2024-05-05 | 2026-08-28 | 2026-06-30 | Not Yet Approved |  |  | 0 | 0 | 0 | Jason Hill | Shubham Nallamuthu